## summary
group | concept | requested | revised project
materials and services | ISO TC69 Standards | 0 | Own resources and other contributors
materials and services | AIAG Manuals acquisition | 0 | Own resources and other contributors
materials and services | Shiny server | 0 | Contributing companies
materials and services | github | 0 | Free academic version
materials and services | Development laptop | 0 | Contributing companies
people | Senior researchers | 5090.9091 | Revised scope
people | Junior researcher | 9804.36 | Revised scope + contributing company
travel | R/Stats conferences | 0 | Own resources
travel | ISO/Industry events | 0 | Own resources
direct | Total direct costs | 14895.2691 | Direct costs requested
indirect | Indirect costs (21%) | 3128.0065 | University rules
total | Total cost | 18023.2756 | Total requested

## WP
wp | title | starts | ends | milestones
WP1 | Infrastructure building | M1 | M3 | Github repo with classes, data structures and shiny basic demo
WP2 | Infrastructure development | M4 | M11 | Progress reports, github package releases for each group of methods
WP3 | Infrastructure deployment and validation | M7 | M12 | CRAN submits and shiny app update for each group of methods
WP4 | Dissemination and coordination | M1 | M12 | Dissemination activities reports for each group of methods

## tasks
WP | Task | Task title | starts | ends | hours | senior_hours_y1 | junior_hours_y1 | senior_hours_y2 | junior_hours_y2 | S1 | J1 | S2 | J2 | S3 | J3 | S4 | J4 | S5 | J5 | S6 | J6 | S7 | J7 | S8 | J8 | S9 | J9 | S10 | J10 | S11 | J11 | S12 | J12 | S13 | J13 | S14 | J14 | S15 | J15 | S16 | J16 | S17 | J17 | S18 | J18 | S19 | J19 | S20 | J20 | S21 | J21 | S22 | J22 | S23 | J23 | S24 | J24
WP1 | T1.1 | Standards' Library gathering | M1 | M1 | 20 | 4 | 16 | 0 | 0 | 4 | 16
WP1 | T1.2 | Configure R Studio project, github repo, mail list, and webpage | M1 | M1 | 19 | 4 | 15 | 0 | 0 | 4 | 15
WP1 | T1.3 | Design quality data standard implementation | M1 | M1 | 30 | 6 | 24 | 0 | 0 | 6 | 24
WP1 | T1.4 | Define and document classes and generic methods | M1 | M2 | 56 | 8 | 48 | 0 | 0 | 6 | 18 | 2 | 30
WP1 | T1.5 | Define and document standards' verification process | M2 | M3 | 80 | 10 | 70 | 0 | 0 |  |  | 4 | 30 | 6 | 40
WP1 | T1.6 | Define and document functions common structure | M2 | M3 | 51 | 6 | 45 | 0 | 0 |  |  | 2 | 20 | 4 | 25
WP1 | T1.7 | Build shiny basic demo | M3 | M3 | 46 | 6 | 40 | 0 | 0 |  |  |  |  | 6 | 40
WP2 | T2.1 | Implementation of Control Charts Standards | M4 | M6 | 332 | 30 | 302 | 0 | 0 | [6 empty] | 10 | 86 | 10 | 108 | 10 | 108
WP2 | T2.2 | Implementation of Capability Analysis Standards | M7 | M9 | 170 | 20 | 150 | 0 | 0 | [12 empty] | 10 | 60 |  |  | 10 | 90
WP2 | T2.3 | Implementation of Measurement Systems Analysis Standards | M10 | M12 | 193 | 12 | 181 | 0 | 0 | [18 empty] | 6 | 85 | 6 | 96
WP2 | T2.4 | github major releases (at least for each group) | M4 | M12 | 76 | 8 | 68 | 0 | 0 | [6 empty] | 2 | 6 |  |  |  |  | 2 | 6 | [6 empty] | 2 | 6 | 2 | 50
WP3 | T3.1 | Validation of implemented methods | M7 | M12 | 74 | 14 | 60 | 0 | 0 | [12 empty] | 8 | 20 |  |  |  |  | 4 | 10 |  |  | 2 | 30
WP3 | T3.2 | Releases to CRAN | M8 | M12 | 42 | 4 | 38 | 0 | 0 | [16 empty] | 2 | 18 |  |  |  |  | 2 | 20
WP3 | T3.3 | Shiny UI design for each method (validation) | M10 | M13 | 22 | 2 | 20 | 0 | 0 | [18 empty] | 2 | 20
WP3 | T3.4 | Shiny UI design for each method (new data) | M11 | M14 | 22 | 2 | 20 | 0 | 0 | [20 empty] | 2 | 20
WP3 | T3.3 | Minor Releases to github | M21 | M12 | 6 | 0 | 6 | 0 | 0 | [23 empty] | 6
WP4 | T4.1 | WP1 Training and coordination | M1 | M3 | 159 | 28 | 131 | 0 | 0 | 12 | 60 | 8 | 48 | 8 | 23
WP4 | T4.2 | WP1 reporting and dissemination | M4 | M4 | 20 | 4 | 16 | 0 | 0 | [6 empty] | 4 | 16
WP4 | T4.3 | WP2 training and coordination | M4 | M12 | 131 | 35 | 96 | 0 | 0 | [6 empty] | 6 | 20 | 6 | 20 | 5 | 20 | 4 | 8 |  |  | 4 | 6 | 3 | 8 | 3 | 8 | 4 | 6
WP4 | T4.4 | WP2 reporting and dissemination | M7 | M12 | 41 | 7 | 34 | 0 | 0 | [12 empty] | 2 | 20 |  |  |  |  | 3 | 8 |  |  | 2 | 6
WP4 | T4.5 | WP3 training and coordination | M7 | M12 | 72 | 10 | 62 | 0 | 0 | [12 empty] | 2 | 20 |  |  | 2 | 20 | 2 | 8 | 2 | 8 | 2 | 6
WP4 | T4.6 | WP3 reporting and dissemination | M8 | M12 | 12 | 4 | 8 | 0 | 0 | [16 empty] | 2 | 4 |  |  |  |  | 2 | 4
|  | Total planned | M1 | M12 | 1674 | 224 | 1450 | 0 | 0 | 32 | 133 | 16 | 128 | 24 | 128 | 22 | 128 | 16 | 128 | 15 | 128 | 28 | 134 | 0 | 0 | 20 | 138 | 20 | 139 | 15 | 138 | 16 | 128 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 5091.52 |  | 0

## People
Group | Name | Affiliation
senior researcher | Emilio López Cano | University of Castilla-La Mancha
senior researcher | Noelia García Rubio | University of Castilla-La Mancha
senior researcher | Matías Gámez Martínez | University of Castilla-La Mancha
senior researcher | Esteban Alfaro | University of Castilla-La Mancha
senior researcher | José Luis Alfaro | University of Castilla-La Mancha
junior researcher | To be contracted | University of Castilla-La Mancha
academic collaborator | Víctor Manuel Casero Alonso | University of Castilla-La Mancha
academic collaborator | Virgilio Gómez-Rubio | University of Castilla-La Mancha
academic collaborator | Javier M. Moguerza | Rey Juan Carlos University
academic collaborator | Andrés Redchuk | Rey Juan Carlos University
industry collaborator | Austin Cox | Honeywell (USA)
industry collaborator | Mariano Prieto | ENUSA (Spain)
industry collaborator | Luc Castermans | Philips (The Netherlands)
industry collaborator | Garry Kitchin | BNL (UK)
industry collaborator | Diana Kardys | u-blox (Switzerland)
academic collaborator | María Villeta | Complutense University
industry collaborator | Juan Riera | Lactalis Groupe

## facts
| Ayudante | CD
Coste anual | 19608.77 | 40000
2% | 20000.9454 | 40000
mes | 1634.06
neto mes | 1034.53
horas año | 1540 | 1760
coste hora | 12.9876 | 22.7273
horas mes totales | 128.3333 | 146.6667
total horas | 1540 | 224
horas mes proyecto | 140 | 20.3636
c.i. míos | 1032.2421
meses contrato | 6
Coste | 9804.36
meses proyecto | 11 | (+1)

## Dissemination
stakeholder | web | mail | submission_form
SEIO | http://www.seio.es/ | oficina@seio.es
The World of Statistics | http://www.worldofstatistics.org/ |  | http://www.worldofstatistics.org/wos/submitarticle.cfm